## Sheet1
Question type | unit_id | Question name | Question text | general feedback | default garde | penalty | hidden | idnumber | single | shuffle | answering number | instruction | correct feedback | partially | incorrect | Fraction | answer1 | feedback1 | fraction2 | answer2 | feedback2 | fraction 3 | answer3 | feedback3 | fraction 4 | answer4 | feedback4
multichoice | 26,28 | Q1 | In a large corporation, coaching, guiding and mentoring for a typical Six Sigma project are responsibility of | All four answers could potentially be true. However, since a large corporation is referenced, then master black belts are probably present and the question most clearly defines their role | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | Master Black Belt | All four answers could potentially be true. However, since a large corporation is referenced, then master black belts are probably present and the question most clearly defines their role | 0 | Process owner | All four answers could potentially be true. However, since a large corporation is referenced, then master black belts are probably present and the question most clearly defines their role | 0 | Black Belt | All four answers could potentially be true. However, since a large corporation is referenced, then master black belts are probably present and the question most clearly defines their role | 0 | Team Leader | All four answers could potentially be true. However, since a large corporation is referenced, then master black belts are probably present and the question most clearly defines their role
multichoice | 26 | Q2 | A breakdown of CTQ requirements is accomplished using a diagram containing critical needs, drivers and metrics (CTQs). This diagram or structure is called? | The diagram is typical of a CTQ tree diagram or CTQ drill-down tree diagram | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | A CTQ drill-down tree diagram or CTQ tree diagram | The diagram is typical of a CTQ tree diagram or CTQ drill-down tree diagram | 0 | A CTQ Gantt chart | The diagram is typical of a CTQ tree diagram or CTQ drill-down tree diagram | 0 | A CTQ Pareto chart | The diagram is typical of a CTQ tree diagram or CTQ drill-down tree diagram | 0 | A CTQ Process map | The diagram is typical of a CTQ tree diagram or CTQ drill-down tree diagram
multichoice | 26 | Q3 | Which of the following element is part of project charter? | Usually, a project charter contains problem statement, goal statement or objective, team members and their roles, project scope, and benefits. Project charter doesn’t contain any solutions, causes or root causes or data collection plan. | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | Project scope | Usually, a project charter contains problem statement, goal statement or objective, team members and their roles, project scope, and benefits. Project charter doesn’t contain any solutions, causes or root causes or data collection plan. | 0 | Brain stormed solutions | Usually, a project charter contains problem statement, goal statement or objective, team members and their roles, project scope, and benefits. Project charter doesn’t contain any solutions, causes or root causes or data collection plan. | 0 | Root causes | Usually, a project charter contains problem statement, goal statement or objective, team members and their roles, project scope, and benefits. Project charter doesn’t contain any solutions, causes or root causes or data collection plan. | 0 | Data collection plan | Usually, a project charter contains problem statement, goal statement or objective, team members and their roles, project scope, and benefits. Project charter doesn’t contain any solutions, causes or root causes or data collection plan.
multichoice | 26 | Q4 | Which of the following scenarios would be least likely to follow the Pareto Principle: | Note that a negative response is requested. Any of the above items could happen. But Options A, C and D have been found to be true in a large number of organizations. Option B is more likely the correct answer. | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | 20% of the machines will produce 80% of the products | Note that a negative response is requested. Any of the above items could happen. But Options A, C and D have been found to be true in a large number of organizations. Option B is more likely the correct answer. | 0 | 20% of the causes creates 80% of the problem | Note that a negative response is requested. Any of the above items could happen. But Options A, C and D have been found to be true in a large number of organizations. Option B is more likely the correct answer. | 0 | 20% of the customer will lodge 80% of complaints | Note that a negative response is requested. Any of the above items could happen. But Options A, C and D have been found to be true in a large number of organizations. Option B is more likely the correct answer. | 0 | 80% of complaints will fall in 20% of the defect categories | Note that a negative response is requested. Any of the above items could happen. But Options A, C and D have been found to be true in a large number of organizations. Option B is more likely the correct answer.
multichoice | 26 | Q5 | Which of the following would build on the basic financial statement to explain why, specifically the problem must be solved now? | The business case might also be referred to as the financial drivers behind a project. You would build on that basic financial statement to explain why, specifically, the loss of money, efficiency, or quality is important to consumers, employees, or the organization. You might also make an argument for why the problem must be solved now; in essence, why is this project being run now in place of another project? | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | Business case | The business case might also be referred to as the financial drivers behind a project. You would build on that basic financial statement to explain why, specifically, the loss of money, efficiency, or quality is important to consumers, employees, or the organization. You might also make an argument for why the problem must be solved now; in essence, why is this project being run now in place of another project? | 0 | Problem Statement | The business case might also be referred to as the financial drivers behind a project. You would build on that basic financial statement to explain why, specifically, the loss of money, efficiency, or quality is important to consumers, employees, or the organization. You might also make an argument for why the problem must be solved now; in essence, why is this project being run now in place of another project? | 0 | Scope | The business case might also be referred to as the financial drivers behind a project. You would build on that basic financial statement to explain why, specifically, the loss of money, efficiency, or quality is important to consumers, employees, or the organization. You might also make an argument for why the problem must be solved now; in essence, why is this project being run now in place of another project? | 0 | SIPOC | The business case might also be referred to as the financial drivers behind a project. You would build on that basic financial statement to explain why, specifically, the loss of money, efficiency, or quality is important to consumers, employees, or the organization. You might also make an argument for why the problem must be solved now; in essence, why is this project being run now in place of another project?
multichoice | 26 | Q6 | Successful projects have a well-defined scope that is approved and backed by a project sponsor or champion | TRUE | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | TRUE | TRUE | 0 | FALSE | TRUE | 0 |  | TRUE | 0 |  | TRUE
multichoice | 26 | Q7 | Which of the following tool is a quick and easy method to define In and Out Scope of project or process | The In and Out of the Box method is a quick and easy method that helps teams define project or process scope | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | Box Method | The In and Out of the Box method is a quick and easy method that helps teams define project or process scope | 0 | Cause-and-Effect Diagram | The In and Out of the Box method is a quick and easy method that helps teams define project or process scope | 0 | Hypothesis testing | The In and Out of the Box method is a quick and easy method that helps teams define project or process scope | 0 | Control Chart | The In and Out of the Box method is a quick and easy method that helps teams define project or process scope
multichoice | 26 | Q8 | In SIPOC, what P – stands for? | In SIPOC, S – Suppliers, I – Input, P – Process, O – Output and C – Customer | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | Process | In SIPOC, S – Suppliers, I – Input, P – Process, O – Output and C – Customer | 0 | Power | In SIPOC, S – Suppliers, I – Input, P – Process, O – Output and C – Customer | 0 | Project | In SIPOC, S – Suppliers, I – Input, P – Process, O – Output and C – Customer | 0 | Project map | In SIPOC, S – Suppliers, I – Input, P – Process, O – Output and C – Customer
multichoice | 26 | Q9 | What is the best definition of RTY? | Rolled throughput yield is the cumulative calculation of yield through multiple steps | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | The cumulative calculation of yield through multiple steps | Rolled throughput yield is the cumulative calculation of yield through multiple steps | 0 | Significant differences in individual yields | Rolled throughput yield is the cumulative calculation of yield through multiple steps | 0 | The drop in yield at the worst process step | Rolled throughput yield is the cumulative calculation of yield through multiple steps | 0 | The total yield output of multiple processes | Rolled throughput yield is the cumulative calculation of yield through multiple steps
multichoice | 26 | Q10 | The Pareto chart is a widely used quality tool. The principles of Pareto analysis have been used in many projects. Which of the following statements is an inappropriate application of a Pareto chart? | Note that a negative response is requested. Pare to charts are commonly used to display category occurrences (answer A). Pareto charts can be constructed to evaluate the criticality of financial impact of each category (answers C and D). An alphabetic ranking of categories makes no sense at all | 1 | 0.33333 | 0 |  | TRUE | TRUE | ABCD | 0 | Your answer is correct. | Your answer is partially correct. | Your answer is incorrect. | 100 | An alphabetic based ranking of categories | Note that a negative response is requested. Pare to charts are commonly used to display category occurrences (answer A). Pareto charts can be constructed to evaluate the criticality of financial impact of each category (answers C and D). An alphabetic ranking of categories makes no sense at all | 0 | A frequency based ranking of categories | Note that a negative response is requested. Pare to charts are commonly used to display category occurrences (answer A). Pareto charts can be constructed to evaluate the criticality of financial impact of each category (answers C and D). An alphabetic ranking of categories makes no sense at all | 0 | A criticality weighted ranking of categories | Note that a negative response is requested. Pare to charts are commonly used to display category occurrences (answer A). Pareto charts can be constructed to evaluate the criticality of financial impact of each category (answers C and D). An alphabetic ranking of categories makes no sense at all | 0 | A financially weighted ranking of categories | Note that a negative response is requested. Pare to charts are commonly used to display category occurrences (answer A). Pareto charts can be constructed to evaluate the criticality of financial impact of each category (answers C and D). An alphabetic ranking of categories makes no sense at all