## Sheet1
Q. No. | Exam_Sim | Level | content_id | Chapter | Question Type | question_text | Correct Option | Option 2 | Option 3 | Option 4 | Rationale
Q1 | Exam Sim 1 | Level1 | 59 | Introduction | Fill Blank | A P3O can significantly _______________ an organization’s chances of successfully delivering its strategy, ______________ benefits and delivering programmes and projects more cost-effectively. | Increase, Maximizing | Decrease, Minimizing | Maximizing, Increase | Minimizing, Decrease | A P3O can significantly increase an organization’s chances of successfully delivering its strategy, maximizing benefits and delivering programmes and projects more cost-effectively.
Q2 | Exam Sim 1 | Level1 | 59 | Introduction | Fill Blank | Implementation of the P3O model may be managed as a series of small incremental business changes, delivered as part of ______________________ | Business as usual | Project Management | P3O Management | Office Management | Implementation of the P3O model may be managed as a series of small incremental business changes, delivered as part of business as usual.
Q3 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | Is the business investing in those programmes and projects that make the greatest contribution to achieving corporate strategy? | Business change strategy | Project strategy | Portfolio Strategy | Programme Strategy | This is one of the question being asked when Governance model focus on Business change strategy
Q4 | Exam Sim 1 | Level1 | 59 | Introduction | Fill Blank | Ensure the right decisions are escalated to the right people with relevant information to support the _____________________ | Decision-making process | Project-making process | Office-making process | P3O Process | Ensure the right decisions are escalated to the right people with relevant information to support the decision-making process
Q5 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | Who are responsible for providing investment for designing and implementing the P3O model? | Senior managers | Operations Manager | Office Manager | Executive | Senior managers responsible for providing investment for designing and implementing the P3O model will want to see some personal success as an incentive for supporting the change.
Q6 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | Which of skills and competencies are centrally managed for portfolio, programme and project management across the organization. | Training and the development | Learning and the development | Research and the development | None of the above | Training and the development of skills and competencies are centrally managed for portfolio, programme and project management across the organization.
Q7 | Exam Sim 1 | Level1 | 59 | Introduction | Fill Blank | _________________________ is supported through management reporting at a highlight level or by exception and gated reviews. | Strategic governance and senior stakeholder engagement | Strategic report and Junior stakeholder engagement | Strategic report and Project engagement | Strategic governance and Programme management | Strategic governance and senior stakeholder engagement is supported through management reporting at a highlight level or by exception and gated reviews.
Q8 | Exam Sim 1 | Level1 | 59 | Introduction | MCQMA | Which one in the organization will either facilitate or inhibit its ability to adopt a P3O approach? | Culture | Employee | Project | Strategy | The culture of the organization will either facilitate or inhibit its ability to adopt a P3O approach. Anyone seeking to develop a new P3O model or enhance an existing one should not underestimate how difficult it may be to change the culture
Q9 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | What are agreed at the appropriate management level and contribute to at least one strategic objective? | Changes to business as usual | Strategic decisions | Resources and changes | An active and iterative process | Changes to business as usual are agreed at the appropriate management level and contribute to at least one strategic objective
Q10 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | What is the Barrier when there are Lack of clarity in P3O offices? | Scope | Cost | Time | Quality | Lack of clarity in the scope of individual P3O offices
Q11 | Exam Sim 1 | Level1 | 59 | Introduction | Fill Blank | The _______________________ may be part of a portfolio office or exist as a separate independent office | Centre of excellence | Programme office | Project office | None of the above | The COE may be part of a portfolio office or exist as a separate independent office
Q12 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | This is the permanent setup in P3O | Hub portfolio office | Programme office | Project office | None of the above | Hub portfolio office, A permanent office set up to support the definition and delivery of a portfolio of programmes and projects within a department, division, geographical region or business unit
Q13 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | This office supports the definition and delivery of a portfolio of change across the entire organization or enterprise | Organization portfolio office | Project office | Programme office | All of the above | A permanent office set up to support the definition and delivery of a portfolio of change across the entire organization or enterprise
Q14 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | Which one of these called as a single permanent office? | Combined functions and services | Isolated functions and services | This may be easier to implement | Consolidation and summarization of progress information | An organization may choose to combine functions and services from a number of the elements of the P3O model to create a P3O which is a single permanent office.
Q15 | Exam Sim 1 | Level1 | 59 | Introduction | MCQSA | Who does provide a range of services to define the standards and provide appropriate tools across PPM functions? | COE | Hub Office | Executive | None of the above | Centre of Excellence (COE) provides a range of services to define the standards and provide appropriate tools across PPM functions.
Q16 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | This one of the focus of Governance model? | Business change value | Business Benefit value | Reporting system | Regular meetings with Team | Business change value is one of the focus Governance model
Q17 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | In which organization P3O is one or two individuals? | Small organizations | Larger organization | Matrix organisation | All of the above | In small organizations where the P3O is simply one or two individuals
Q18 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | This is one of the principle describing All investments have a valid business case throughout the lifecycle and investment funds are awarded on the basis of realizable benefits | Safeguard value | Business change value | Governance | Business Benefit value | Safeguard value is A gated decision process, periodically re-evaluating the ongoing viability of the business case and ensuring benefits continue to be tracked and realized at the planned levels
Q19 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | Fill Blank | A P3O can advise on skills and capability assessments, This is _______________ principle | Invest in people and process | Invest in Assets | Invest in management | None of the above | Invest in people and process is Recognition of portfolio, programme and project disciplines; acknowledgement of the link between strategy and programme and project execution
Q20 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | T or F | Consolidating the requirements across all of the business units may identify that investing in an organization-wide programme of improvement may deliver greater value; True or False? | TRUE | FALSE |  |  | This is TRUE about Consolidating the requirements across all of the business units
Q21 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | Fill Blank | The P3O value matrix Provides a ___________ | High-level description | Mid-level description | Decision-making process | Culture | It provides a high-level description of the potential role a P3O can play in providing governance over both enabling and restraining activities, across the three levels.
Q22 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | Who is looking for timely and concise information to enable them to make appropriate investment decisions? | Senior managers | Operations Manager | Office Manager | Employee | Senior managers always look for timely and concise information to enable them to make appropriate investment decisions
Q23 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | Who does own the vision of P3O? | Sponsor | Senior managers | COE | Organization | The P3O vision will be owned by the P3O sponsor and agreed by the key stakeholders.
Q24 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | Fill Blank | All investment is subject to ____________ to support successful delivery | Gated reviews | Execution | Planning | Closing | All investment is subject to gated reviews to support successful delivery.
Q25 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | Which one of theses focus on growth as well as keeping business as usual happy and able to function effectively? | A balanced portfolio | A balanced Programme | A balanced Project | Reduced risk | A balanced portfolio focus on growth as well as keeping business as usual happy and able to function effectively
Q26 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | How can we reduce the management overhead dealing with prioritization conflicts for resources? | Proactive identification and resolution of conflicts and competition for scarce and costly resources | Proactive investment and resolution of conflicts and competition for scarce and costly resources | Reactive identification and resolution of conflicts and competition for scarce and costly resources | Reactive identification of investment and resolution of conflicts and costly resources | Proactive identification and resolution of conflicts and competition for scarce and costly resources
Q27 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | T or F | The costs of the P3O are projected at the commencement of the financial period, and a value for each service is agreed. | TRUE | FALSE |  |  | This is TRUE about the costs of P3O
Q28 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | Fill Blank | 75% of projects completing in 3 months will have benefits tracked against the benefits realization plan and will be reported on monthly, This is an example KPI of ___________ | Enhanced contribution | Specific, Measurable, Achievable, Relevant and Time-bound. | Improved portfolio balance | Budget restrictions | Enhanced contribution to strategic objectives. Improving the portfolio balance will involve not only developing the right mix of programmes and projects but also avoiding the scenario where multiple programmes and projects:
Q29 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | What are the things to be considered to made when we deliver new or revised P3O model using existing organizational funding availability? | Capability and capacity | Investment | Resources | Market analysis | Capability and capacity: Depending on the funding available, the new or revised P3O model may have to be delivered using existing organizational capability and capacity
Q30 | Exam Sim 1 | Level1 | 79 | Why have a P3O? | MCQSA | In which office the classification of expenses will go by the financial rules set up for the programme or project? | Temporary offices | Permanent offices | COE | Hub Office | In Temporary offices the classification of expenses will go by the financial rules set up for the programme or project.
Q31 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one of these functional area aims on endorsing the delivery of change? | Delivery support | Scrutiny and challenge | Project support | None of the above | Delivery support functions aims on endorsing the delivery of change
Q32 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which office supports on local need and ensure adherence to a steady organization-wide set of standards? | Decentralized office | Centralized Office | COE | All of the above | Decentralized Model office supports on local need and ensure adherence to a steady organization-wide set of standards
Q33 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | Fill Blank | Facilitate programme and project kick off is the roles of______________ | Delivery functions | Portfolio functions | Centre of excellence functions | Project office | Delivery support functions facilitates the programme and project kick off
Q34 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one of these is primary focus of Organization portfolio offices? | Strategic planning and portfolio support services | Capability and capacity Establishment | Business Benefit value | Project strategy | Organization portfolio offices focus on Strategic planning and portfolio support services as primary
Q35 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | T or F | The P3O should not develop a risk management policy for compliance | FALSE | TRUE |  |  | The P3O should develop a risk management policy for compliance by programmes and projects based on the organization’s own corporate risk policy
Q36 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who does ensure senior management decisions lead to the fulfilment of strategic objectives through the delivery of programmes and projects? | Portfolio analyst | Project officer | Change control | Quality assurance | Portfolio analyst role facilitates the development and ongoing management of an optimized portfolio, ensuring senior management decisions lead to the fulfilment of strategic objectives through the delivery of programmes and projects
Q37 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who does seek to continuously improve performance of the portfolio, programme and projects within an organization? | Consultancy and performance management | Information management | Change control | None of the above | Consultancy and performance management role seeks to improve the performance of the portfolio continuously, programme and projects within an organization
Q38 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | What are basis for P3O sizing? | Budget, Headcount, Function | Budget, Investment, Function | Budget, Benefit, Change | All of the above | P3O sizing is decided basis of Budget, Headcount, Function
Q39 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who will work with the programme or project manager and the business to help define an appropriate level of governance and structure for effective management? | Internal consultant | External consultant | Portfolio analyst | Project officer | Programme or project specialist (internal consultant) helps to define an appropriate level of governance and structure for effective management
Q40 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who will provide strategic overview and scrutiny, ensuring alignment with wider policy? | Head of programme | Project officer | Internal consultant | External consultant | Strategic overview and scrutiny, ensuring alignment with wider policy are provided by Head of programme or project office (temporary office)
Q41 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | Fill Blank | Big picture is often referred as_________ | Helicopter view | Eagle view | Fish view | None of the above | The ‘big picture’ is referred to as the ‘helicopter view’, and make recommendations based on insightful information
Q42 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one these looking to improve the potential for successful delivery? | Assurance function | Project | Environment | Deliverable | An assurance function should always be forward-looking and action-oriented (either specific or systemic) to improve the potential for successful delivery, rather than simply auditing what may have happened.
Q43 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | What is the reason for the failure of permanent P3Os? | Lack of integration | Investment | Employee | Resources | A frequent reason for the failure of permanent P3Os is a lack of integration of the P3O model with the wider organization model.
Q44 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | This is True about P3O | A P3O provides a decision-enabling/delivery support structure for change within an organization. | A P3O provides a framework for Project management outside the organization | A P3O does not provide a decision-enabling/delivery support structure for change within an organization. | None of the above | A P3O provides a decision-enabling/delivery support structure for change within an organization.
Q45 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | Fill Blank | The Portfolio functions focus on _____________ | Prioritization and Benefits | Good practice | Training and coaching | Capacity planning | The Portfolio functions focus on Prioritization and Benefits
Q46 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | T or F | Temporary portfolio or hub portfolio offices, where Permanent programme or project offices are formed to support proposals as they close, generally have high PPM maturity, True or False: | FALSE | TRUE |  |  | Organizations that have no organization portfolio or hub portfolio offices, where temporary programme or project offices are established to support initiatives as they arise, generally have low PPM maturity
Q47 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | which one these a consequences of not doing a stable approach to programme and project management training through the obtaining of an authorized set of courses and training providers? | Staff select which courses they wish to attend, and there are inconsistencies in language and messages | Consistent training messages and language | Training and coaching | None of the above | Staff select which courses they wish to attend, and there are inconsistencies in language and messages
Q48 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which on these required to be developed by P3O for compliance by programmes and projects? | Risk management policy | Quality control policy | Resource control policy | Deliverable policy | The P3O should develop a risk management policy for compliance by programmes and projects
Q49 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one these is part of portfolio planning? | Stakeholder engagement and communications | Issue management | Reporting | Internal consultancy | Stakeholder engagement and communications are part of portfolio planning
Q50 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | This is one of the functions of Delivery: | Quality assurance | Performance monitoring | Internal consultancy | Performance monitoring | Quality assurance: Organization assurance that programmes and projects have suitable quality plans and measures. This is a function Delivery
Q51 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Where the programme-level risk is considered? | Within Delivery | Within Portfolio | Within Programme | None of the above | Within the delivery support functional area, programme-level risk is considered
Q52 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who does provide administrative support in P3O? | Secretariat | Executive | Champion | Sponsor | The secretariat/administrator role provides portfolio, programme or project administrative support.
Q53 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who is accountable for developing and maintaining a viable business case to secure the investment required to implement and run the P3O model? | Sponsor | Champion | Executive | Secretariat | Sponsor is accountable for developing and maintaining a viable business case to secure the investments
Q54 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Centre of excellence focuses on except: | Information management | Internal consultancy | Standards and methods | Organizational learning and knowledge management | Information management is function of Delivery and it's not part of Centre of excellence focus
Q55 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one of these is the totality of an organisation’s financing in the changes required to accomplish its strategic objectives? | A portfolio | A P3O | A Programme | All of the above | A portfolio is the totality of an organisation’s financing in the changes required to accomplish its strategic objectives
Q56 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | Fill Blank | Perform current state assessment, prepare outline vision statement, objectives and goals, outline business case including risks are part of _______________ | Identify | Close | Deliver | Quality | In Identify process, we Perform current state assessment, prepare outline vision statement, objectives and goals, outline business case including risks
Q57 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Who is responsible to enhance the planning and delivery process by collecting and maintaining data in a steady form? | Project Officer | Executive | Portfolio analyst | None of the above | Programme or Project Officer (Co-ordinator or administrator) responsible to enhance the planning and delivery process by collecting and maintaining data in a steady form
Q58 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | In which office the planning is concerned with the provision of standards? | COE | CEO | COOE | HOE | Within the centre of excellence functional area, planning is concerned with the provision of standards
Q59 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | T or F | Programmes and projects will use guidelines and assurance from the business COE or the local hub portfolio office depending on its size and maturity. | TRUE | FALSE |  |  | Programmes and projects will use guidelines and assurance from the business COE or the local hub portfolio office depending on its size and maturity.
Q60 | Exam Sim 1 | Level1 | 80 | Designing a P3O Model | MCQSA | Which one of these describes a system of organizational design where there is a permanent central organization portfolio office connected to a number of permanent decentralized offices? | Hub-and-Spoke | Decentralized | Centralized | All of the above | This is the description of Hub-and-spoke Model
Q61 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which of these is used in programme for The implementation of P3O? | MSP | PRINCE2 | M_O_V | P3O | Managing Successful Programmes (MSP) is used in programme for The implementation of P3O
Q62 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | When do we establish and improve the capability and the role of the P3O model? | Implementation lifecycle | P3O lifecycle | Project lifecycle | Hub recycle | A P3O implementation lifecycle for establishing/ improving capability and the role of the P3O model, based on MSP principles and processes
Q63 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | which one of these is part of Deliver phase? | Realize benefits and Reviews | Blueprint and Benefits | Objectives and goals | Close | Realize benefits and Reviews are part of Deliver phase
Q64 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | This is one of the key activity within define process? | Identify and analyse stakeholders | Realize benefits and Reviews | Outline business case | All of the above | In Define process, Identification and stakeholders analyse are conducted
Q65 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these is to include the objectives and structure of the future P3O model through an outline vision statement and programme brief? | Identify | Close | Execute | All of the above | Identify process to include the objectives and structure of the future P3O model through an outline vision statement and programme brief
Q66 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | This is to Evaluate the change in the organization’s level of_____________ as a result of investment in the P3O model over time. | P3M3 Maturity | Quality Assessment | Performance assessment | None of the above | P3M3 assessment is to Evaluating the change in the organization’s level of P3M3 maturity as a result of investment in the P3O model over time
Q67 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one these is not culture an effective P3O model? | Change control | Service-focused | Information sharing | Innovative | Change control is the management control characteristics and It's not culture an effective P3O model
Q68 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | Achieving higher returns on investment in business change is called as ____________ | Maximization of opportunities | Maximization of Threats | Maximization of Strengths | Maximization of Risk | Achieving higher returns on investment in business change is called as Maximization of opportunities
Q69 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who does review the Portfolio report? | Senior management | Portfolio director | Executive | Employee | Portfolio report is a management dashboard with supporting papers, including benefits reviews submitted to Senior management
Q70 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who is accountable for management dashboard? | Portfolio office manager | Champion | Employee | Manager | Portfolio office manager is accountable for management dashboard; The objective of the management dashboard technique is to provide key decision-support information across a portfolio using highlight and exception-based reporting
Q71 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one these is prepared by Programme and project boards? | Escalated programme and project risk and issue papers | Mission-critical business cases | Management dashboard | Project report | Escalated programme and project risk and issue papers are prepared by Programme and project boards
Q72 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who does review Escalated programme and project risk and issue papers? | Business unit senior manager | Portfolio office manager | Manager | Executive | Business unit senior manager reviews the Escalated programme and project risk and issue papers
Q73 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these prepared by Project manager? | Highlight and exception reports | Salary statement | Project statement | All of the above | Project manager is accountable for Highlights and exception reports; Highlight reports may be monthly or fortnightly on acceptance of project business case
Q74 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | When will the functions and services realize the anticipated benefits? | The right skills and experience should be provided | Visible support | Detailed costings for the resources and tools | Revise the scope | Functions and services will only realize the anticipated benefits if they are provided by individuals with the right skills and experience.
Q75 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | What does need to be done if there is no senior management consensus on the P3O vision? | Revise the scope to what is acceptable and supportable by a viable business case. | Proceed the scope to what is acceptable and supportable by a viable business case. | Escalate to COE level | Do nothing | If there is no senior management consensus on the P3O vision then Revise the scope to what is acceptable and supportable by a viable business case.
Q76 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Why do we have the portfolio Planning? | To develop a balanced portfolio of programmes and projects | To close a balanced portfolio of programmes and projects | To deliver a balanced portfolio of programmes and projects | None of the above | we have the portfolio Planning to develop a balanced portfolio of programmes and projects
Q77 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | A P3O programme with the objective to improve PPM maturity within the organization may include projects to design and establish except: | None of the above | Programme and project stage-gate model and framework | Business planning or strategy translation framework | Requirements management model and framework | None of the above are applicable to a P3O programme with the objective to improve PPM maturity within the organization may include projects to design and establish
Q78 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these is Key sensitivity that may impact on the development of projects dossier? | Risks to delivery and planned benefits | Viable business case | Implementation lifecycle | All of the above | Risks to delivery and planned benefits that may impact on the development of projects dossier
Q79 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these is considered when defining the success factors? | Stakeholder analysis | Control Analysis | Performance assessment | Stakeholder assessment | Ensure that a stakeholder analysis is done early and that a communications plan is developed to ensure consistent messages are being given to all impacted stakeholders
Q80 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | P3O recommends at the end of each stage of delivery, a review should be undertaken to assess progress to date, This is called as _________________ | a ‘go’ or ‘no go’ gate | Running practices | Implement the P3O model | Obtaining a baseline view | P3O’s gated review process to provide governance through a ‘go’ or ‘no go’ gate, demonstrating that you believe in and practise your own processes.
Q81 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who can be involved to fast-track the improvement programme? | External consultants | Project Management | Employee | All of the above | External consultants or contractors are involved to fast-track the improvement programme
Q82 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who is responsible to engage the new resources joining P3O office? | COE | CEO | Hub office | External consultants | COE is responsible for facilitated workshops, the provision of standard processes and coaching
Q83 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | The temporary office may be resourced from central teams Where there is a _______________ | Portfolio office or hub Portfolio office in place | Project office in place | Programme office in place | None of the above | The temporary office may be resourced from central teams with standards and templates provided by a COE function
Q84 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one is not a Key areas of focus for a temporary programme or project office? | None of the above | Information repositories | Budget controls and financial reporting | Funding arrangements | All Information repositories, Budget controls and financial reporting are the Key areas of focus for a temporary programme or project office
Q85 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | When does the temporary office should revisit its processes? | All Over delivery | One time activity | Implementation | Close | The temporary office should revisit its processes and ways of working to ensure they remain the best approaches and are scalable to current information needs
Q86 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Outline vision statement is prepared at the time of P3O __________Process | Identify | Deliver | close | Implement | Outputs from the Identify process include the objectives and structure of the future P3O model through an outline vision statement and programme brief, and guidance on developing a business case
Q87 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these is an increased cost avoidance in P3O model? | Reducing the investment in outputs that do not lead to planned business benefits | Delivering the same capabilities with less business change investment | Reducing investment in programmes and projects | Delivering more change through programmes and projects with the same investment | Increased cost avoidance is Reducing the investment in outputs that do not lead to planned business benefits, and stopping such programmes or projects either before they get off the ground or while they are under way
Q88 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Who is accountable to create Mission-critical business cases? | Senior responsible owners | Project Board | Business unit managers | Business change managers | Senior responsible owners create the Mission-critical business cases
Q89 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | Defined time after project completed when benefits and original business-case investment can be assessed, This is called as ________________ | Post-project report | Transition plan | Benefit profiles | End project report | Post-project report is a Defined time after project completed when benefits and original business-case investment can be assessed
Q90 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | which one of these is impact on the quality of outputs or lead to resistance to change? | Lack of common language among programme team | Overly focusing on processes | Overly focusing on toolsets | Resistance to change | Lack of common language among programme team impacts on the quality of outputs or lead to resistance to change
Q91 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | T or F | Benefits will be realized throughout the programme to implement the P3O model, not just post programme, True or False | TRUE | FALSE |  |  | This is TRUE about Benefits will be realized throughout the programme to implement the P3O model, not just post programme
Q92 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | Fill Blank | A list of all programmes and projects being undertaken by the organization, their link to strategy, value, key stakeholders and delivery timeframe, This is called as __________________ | Portfolio register | Risk Register | Issue register | Quality register | A Portfolio register is a list of all programmes and projects being undertaken by the organization, their link to strategy, value, key stakeholders and delivery timeframe
Q93 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | When P3O owns Delivery resources that are then provided to the business, combined with weak governance arrangements, then the P3O becomes: | De-facto owner of business change | Hub Owner | COE | Project owner | The P3O becomes the de-facto owner of business change When P3O owns Delivery resources that are then provided to the business, combined with weak governance arrangements
Q94 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Why do we implement the P3O model? | To deliver new and consistent processes with goals of improving productivity | To ensure Client paid on time | To provide process with manual intervention | All of the above | To deliver new and consistent processes with goals of improving productivity
Q95 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these plan is prepare by Programme or project manager? | Transition plan | Operations Plan | Closing plan | Risk plan | Transition plan is prepared by Programme or project manager
Q96 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | What do we need to do in order to reduce the treats? | Stronger alignment between planned and actual business change investment | Stronger alignment between planned and actual business change Return of investment | Optimizing investment | investment in programmes | Stronger alignment between planned and actual business change investment
Q97 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | What is the use of Blur print in P3O model? | The blueprint will detail all the data requirements of the P3O to support the various functions and services to be provided | Successful implementation of the P3O model. | To provide too many services across too wide a community with inadequate resourcing will lead to overstretched resources | None of the above | The blueprint will detail all the data requirements of the P3O to support the various functions and services to be provided
Q98 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which model does describe who makes what decisions and when, who may be impacted by those decisions, and what the rules for delegation of authority? | The governance model | The P3O Model | The COE Model | None of the above | The governance model describes that who makes what decisions and when, who may be impacted by those decisions, and what the rules for delegation of authority
Q99 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | At which process we do measure the effectiveness of the P3O in having fit-for-purpose approaches that are used by the programme? | Audits of level of compliance to processes | Governance of level of compliance to processes | Quality of level of compliance to processes | All of the above | In Audits of level of compliance to processes, we do measure the effectiveness of the P3O in having fit-for-purpose approaches that are used by the programme
Q100 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these is measuring the level of satisfaction in the operation of the P3O? | Stakeholder surveys | Quality surveys | Audit surveys | Sampling surveys | Stakeholder surveys is to measure the level of satisfaction in the operation of the P3O
Q101 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | How many members may be involved in a formal implementation of P3O in small organization? | One or Two | many | three or four | five | In a small organization, or where the P3O office consists of only one or two people, there may not be a formal implementation team.
Q102 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | This is part of define process for a permanent P3O model: | Vision statement and Business case | New capability and Realize benefits | Objectives and goals | All of the above | Vision statement and Business case are part of define process for a permanent P3O model
Q103 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these to be included in re-energize of P3O? | An understanding of implementation success factors and key threats to delivery | Providing a one version of the truth | Identifying, understanding and managing | strategies and performance | An understanding of implementation success factors and key threats to delivery
Q104 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Why are we using Technology and data requirements in Define process? | To Develop the P3O blueprint | use case studies | To develop Transition plan | None of the above | we are using Technology and data requirements in Define process to Develop the P3O blueprint
Q105 | Exam Sim 1 | Level1 | 81 | How to implement or re-energize a P3O? | MCQSA | Which one of these also called as measure the effectiveness of risk response actions? | Cost of risk mitigation against level of residual risk | Variance between forecasted benefits | Audits of level of compliance to processes | None of the above | Cost of risk mitigation against level of residual risk is measuring the effectiveness of risk response actions
Q106 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Why do we introduce tools or techniques? | A need for programme and project standardization and data quality | To communicate with stakeholders | Differentiate between the business processes and information | Focus on non-vale added activities | Tools or techniques are needed for programme and project standardization and data quality
Q107 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which systems that map programmes and projects to benefits? | Strategic mapping software | Generic software | management systems | None of the above | Strategic mapping software is a system that map programmes and projects to benefits
Q108 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which tool does benefit the ability to produce integrated reports for multiple audiences from a single set of data? | EPM | PPM | UPM | TPM | EPM benefits the ability to produce integrated reports for multiple audiences from a single set of data
Q109 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This is one of the way of prioritization and optimization: | Multi-criteria analysis | Single-criteria analysis | Tree Analysis | Measurement system Analysis | Multi-criteria analyse is one of the way of prioritization and optimization
Q110 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | What is the purpose of complexity modelling? | To determine the appropriate lifecycle and governance | To Execute the appropriate lifecycle and governance | To Plan the appropriate lifecycle and governance | To Measure the appropriate lifecycle and governance | The purpose of complexity modelling is to determine the appropriate lifecycle and governance
Q111 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which one of these is to determine the dependency network for the identified benefits? | Benefits identification and modelling | Multi-criteria analysis | Tree Analysis | Single-criteria analysis | Benefits identification and modelling is to determine the dependency network for the identified benefits
Q112 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | Fill Blank | A workshop to brainstorm all ____________ from a programme or project at closure, ends of stages or start-up | Lesson sharing | Risk identification | Problem solving | None of the above | Held as a workshop to brainstorm all lessons from a programme or project at closure, ends of stages or start-up.
Q113 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does maintain a stable environment of incremental improvements with periodic change? | Head of P3O | Project Manger | Programme officer | Employee | Head of P3O maintains a stable environment of incremental improvements with periodic change
Q114 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | T or F | P3O should review and challenge the content of documents and templates and offering help where data quality is not as per requirement, True or False: | TRUE | FALSE |  |  | This is TRUE about data quality where it is not as per requirement
Q115 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | How can we measure the regular changes to the baseline? | Earned value analysis | Variance Analysis | Comparative Analysis | All of the above | Earned value analysis is a measurement of regular changes to the baseline
Q116 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | What will happen if the Tool does not match the PPM maturity of the organization? | Detrimental effect on PPM effectiveness | Building blocks | Prioritize multiple projects | Project delivery | If the Tool does not match the PPM maturity of the organization then Detrimental effect on PPM effectiveness will happen
Q117 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | How do we implement the tools? | organizational change programme or stand-alone project | Operations | Business as usual | None of the above | Through an organizational change programme or stand-alone project
Q118 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | What is intent of Tools or Technique? | To meet a specific requirement for an industry or a large client | To ease our job | To increase the time and effort | All of the above | The Intent of Tools or Technique is to meet a specific requirement for an industry or a large client
Q119 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | which one of these not a key strategic benefits of Tools? | Providing a unstructured way to gather information | Reducing cycle times for the collection of decision-support information | Through improved capability to undertake scenario or ‘what if’ analysis on the decision support information | Eliminating or reducing the need for manual data collection, amalgamation, printing and distribution | Providing a unstructured way to gather information
Q120 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | These are Core functions of enterprise PPM tools: | All of the above | Strategic resource planning | Scheduling, tracking and measurement | Programme and project guides and support | All of the given options are Core functions of enterprise PPM tools
Q121 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | How are the systems that used to manage the detailed scope of projects? | Analysing, tracing and prioritizing | Planning, Executing, Closing | analysing, tracing and monitoring | Meeting, tracing and monitoring | Analysing, tracing and prioritizing are the systems that used to manage the detailed scope of projects
Q122 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which one of these model of the organization’s structure, systems and processes? | Enterprise architecture systems | Project architecture systems | Portfolio architecture systems | Programme architecture systems | Enterprise architecture systems is model of the organization’s structure, systems and processes
Q123 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This assessment is a technique that rates the degree of complexity for acquisition-based programmes and projects: | Risk potential assessment | Quality Assessment | Earned value analysis | Comparative Analysis | Risk potential assessment is a technique that rates the degree of complexity for acquisition-based programmes and projects
Q124 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who must be able to develop and maintain effective working relationships with stakeholders? | P3O sponsor | Head of P3O | Portfolio analyst | Programme or project officer | P3O sponsor develops and maintains effective working relationships with stakeholders
Q125 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does Recruit, develop and retain the portfolio office, programme office or COE team? | Head of P3O | Portfolio analyst | Programme or project officer | P3O sponsor | Head of P3O Recruits, develops and retains the portfolio office, programme office or COE team
Q126 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | What is the purpose of the portfolio analyst? | To facilitate the development and ongoing management of an optimized portfolio | Identify dependencies among the programme | Advise on tailoring the templates and procedures to achieve an appropriate project structure | Ensure that the portfolio delivers the organization or departmental strategy | To facilitate the development and ongoing management of an optimized portfolio
Q127 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does play a proactive role in knowledge management to promote programme and project management methods and standards? | Programme or project specialist | Hub Owner | COE | None of the above | Programme or project specialist plays a proactive role in knowledge management to promote programme and project management methods and standards
Q128 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This is one of the approach of the benefits and value role: | Fit for purpose | Quality | Manage | Execute | A consistent ‘fit for purpose’ approach to benefits and value management is applied across the portfolio or programme and that benefits realization is optimized from the organization’s investment in change.
Q129 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which Systems that are used to share learning? | Knowledge management systems | Performance management systems | Requirements management systems | None of the above | Knowledge management systems that are used to share learning
Q130 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This is one of the potential services of temporary programme office: | Constructive challenge, Scrutiny and assessment | Strategic planning for Portfolio | COE support | Hub office support | Constructive challenge, Scrutiny and assessment are services of temporary programme office
Q131 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which one of these is most significant factor in P3O? | Match the complexity of the tools and techniques to the PPM maturity | Strategic planning for Portfolio | Providing a unstructured way to gather information | All of the above | Match the complexity of the tools and techniques to the PPM maturity
Q132 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which are the criteria considered to assess business case approval? | Budget and Timescale | Implement | Lesson sharing | Earned value analysis | Budget, timescale, innovation, number of suppliers, type of customer, brand awareness are considered to assess business case approval
Q133 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | What is the purpose of complexity score? | To determine the recommended governance structures | To implement Operational risk treatment | To ensure Productivity | To Ensure optimized Service delivery | To determine the recommended governance structures and tailored lifecycle for the project
Q134 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | Fill Blank | ___________________________must be applied to the data to ensure that the information provided is trusted? | Appropriate information assurance | Appropriate information control | Appropriate information security | None of the above | Appropriate information assurance must be applied to the data to ensure that the information provided is trusted
Q135 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which one of these does help a groups of people to share and learn together over a period of time? | Communities of practice | Support tools | use a single method | suggested action plans | Communities of practice help a groups of people to share and learn together over a period of time
Q136 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which one will enable portfolio reporting, analysis and decision-making? | Functions and services | Operations | Portfolio | Business as usual | Functions and services will standardize information to aid roll-up and consolidation, enabling portfolio reporting, analysis and decision-making.
Q137 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | In P3O, what is the responsibility of Head of programme? | To develop and maintain robust relationships with all parts of the business | Develop and implement the terms of reference for the COE | Establish access to policy and strategic information for all programmes and projects | Assure the overall integrity and coherence of the portfolio | Head of programme develops and maintains robust relationships with all parts of the business
Q138 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does Escalate issues to the strategy board? | Portfolio analyst | Project Analyst | Project Team | All of the above | Portfolio analyst escalates the issues to the strategy board
Q139 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | T or F | Temporary office Supports the overall integrity and coherence of the programme or project | TRUE | FALSE |  |  | This is TRUE about the support of Temporary office
Q140 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | How does it allow the support on decision against embedded corporate or P3O standards? | Automatic validation | Manual Verification | Automatic approval | Manual approval | Automatic validation of information supports on decision against embedded corporate or P3O standards
Q141 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which is an office that ensures the standards, training, mentoring, coaching, process improvement? | Centre of excellence | Hub Office | Programme office | Project office | Centre of excellence is an office that ensures the standards, training, mentoring, coaching, process improvement
Q142 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which function that owns some corporate function, service, standard? | Design authority | Quality | Programme office | None of the above | Design authority owns some corporate function, service, standard
Q143 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | Fill Blank | The project manager submit a/an _____________ to project board that confirms the handover of all products and provides | End project report | Post-project report | Quality report | Risk report | A report given by the project manager to the project board that confirms the handover of all products and provides an updated business case and an assessment of how well the project has performed against its project initiation documentation.
Q144 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Which on of these technique used to help make decisions about capital expenditure? | Internal rate of return | Benefit cost Analysis | Profit and Loss | Return on Investment | Internal rate of return, It calculates a figure that allows two or more alternative investments to be compared. A larger internal rate of return indicates a better investment.
Q145 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | Fill Blank | ____________Works with the business lead/SRO to define and implement the project governance framework | Head of project | Project Analyst | Project Team | None of the above | Head of project works with the business lead/SRO to define and implement the project governance framework
Q146 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does ensure that a project or programme meets its objectives and delivers the projected benefits? | Senior responsible owner (SRO) | Project Team | Project Analyst | Business as usual | Senior responsible owner (SRO) ensures that a project or programme meets its objectives and delivers the projected benefits
Q147 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This is the Statement that describes the purpose, cost, time and performance requirements, and constraints for a project | Project brief | Project assurance | Programme brief | Programme assurance | Project brief is done to describe the purpose, cost, time and performance requirements, and constraints for a project
Q148 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | This is the decision-enabling and support business model for all business change within an organization: | P3O | PRINCE2 | M_O_V | MSP | Portfolio, Programme and Project Offices (P3O) is the decision-enabling and support business model for all business change within an organization
Q149 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | T or F | A senior manager with appropriate authority who champions the establishment and evolving operation of the P3O is a P3O sponsor | TRUE | FALSE |  |  | This True about P3O sponsor and his accountability
Q150 | Exam Sim 1 | Level1 | 82 | How to operate a P3O? | MCQSA | Who does provide a base data to multiple audiences? | Reporting role | Executive | Project Manager | COE | The purpose of the reporting role is to provide a reporting service to the portfolio, programme or project.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: File Name
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bloom's Level
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bloom's Level
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chapter/Module Name
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make sure the question type should be as same as the real exam. Choose whether the question type is Multiplechoice Single Answer, Mutliple choice multiple answer, True or False, Fill in the blanks type,
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Question Text
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Corrrect option
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incorrect Option
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Explanation for the correct answer